## Gaps to fix
Jenkins Readiness — Gaps to Fix
Remitbee CP Playwright suite · assessed 05 Oct 2026 · edit the yellow Owner, Status and Notes cells
# | Gap | Why it matters | Owner | Priority | Status | Notes
1 | Today's changes are not committed (playwright.flow.config.ts, package.json, run.sh, README) | Jenkins pulls from GitHub, so it would run the old setup: no headless option, Help and Currency Converter not switched off. | Anthony (QA) | High | Open
2 | No Jenkinsfile | Jenkins needs a pipeline: install, run, publish the report. | Claude | High | Open
3 | Saved login cookies are in git (playwright/.auth/*.json) | Live session cookies for the test accounts are on GitHub. The tests do not use them; remove from the repo and add to .gitignore. | Claude | High | Open
4 | Passwords and keys come from .env, which is not in git | They need to be added as Jenkins credentials and passed in as environment variables. | DevOps | High | Open
5 | No JUnit results file | Jenkins needs it to show pass/fail trends and per-test history. One extra reporter line in the config. | Claude | Medium | Open
6 | Retries are 0 | On CI, 1 retry stops a staging hiccup from failing the build. | Claude | Medium | Open
7 | Jenkins machine setup | Needs Node 18+, npx playwright install --with-deps chromium, and network access to cp.wisecapitals.com. | DevOps | High | Open
8 | 6 open failures (SM-06, SM-17, SM-20, PA-29, CE-07, ES-03) | Re-run with one browser first, or the first Jenkins builds will be red. | Anthony (QA) | Medium | Open
| Total gaps | 8
| Done | 0
| Open / in progress / blocked | 8
| % complete | 0%

## Already in place
Jenkins Readiness — Already in Place
What works today without changes
Item | Detail
Code on GitHub | Antonyedward/Remitbee-Playwright-
Headless and parallel runs | HEADLESS=true and --workers=N both work — what a Jenkins machine needs
Reports and evidence | HTML report every run, plus screenshot, video and trace for each failure
Clear entry points | ./run.sh regression headless · npm run flow:smoke:headless
Current quality | Last regression (05 Oct, 16:00): 98.2% of executed tests passed; Help and Currency Converter switched off

## Decisions needed
Jenkins Readiness — Decisions Needed
Fill in the Decision column once agreed
Decision | Who decides | Suggestion | Decision
Which Jenkins (version, Linux agent?) | DevOps
Who adds the credentials (passwords, OTP, API key) | DevOps
Schedule | Anthony / Manager | Smoke after each staging deploy; nightly regression with Send Money and Auth on one browser
Where results go | Anthony / Manager | Jenkins HTML report only, or also email / Slack